## Action Plan Example
ACTION / TASK | ACTION LEAD & PARTNERS | TIMEFRAME | Links to MSC Performance Indicators
|  |  | P1. Target stocks | [6 empty] | P2. Ecosystem components | [14 empty] | P3. Management system
|  |  | 1.1.1 Stock status | 1.1.2 Reference points | 1.1.3 Stock rebuilding | 1.2.1 Harvest Strategy | 1.2.2 Harvest control rules and tools | 1.2.3 Information and monitoring | 1.2.4 Assessment | 2.1.1 Retained spp. status | 2.1.2 Retained spp. management | 2.1.3 Retained spp: Information & monitoring | 2.2.1 Bycatch spp. status | 2.2.2 Bycatch spp. management | 2.2.3. Bycatch spp: Information & monitoring | 2.3.1 ETP spp. status | 2.3.2 ETP spp. management | 2.3.3 ETP spp: Information & monitoring | 2.4.1 Habitat status | 2.4.2 Habitat strategy | 2.4.3 Habitat: information & monitoring | 2.5.1 Ecosystem: status | 2.5.2 Ecosystem: strategy | 2.5.3 Ecosystem: information & monitoring | 3.1.1 Legal or customary framework | 3.1.2 Consultation, roles & responsibilities | 3.1.3 Long-term objectives | 3.1.4 Incentives for sustainable fishing | 3.2.1 Fishery-specific objectives | 3.2.2 Decision-making processes | 3.2.3 Compliance & enforcement | 3.2.4 Research plan | 3.2.5 Management performance evaluation
1. Stock assessment |  |  | (note: H = high priority, M = medium priority, L = low priority according to MSC pre-assessment)
1.1 Develop stock assessment methodology | Client organisation; Research agency | 6 mths | H | M |  | M |  |  | H
1.2 Conduct stock assessment | Research agency | 12 mths | H | M |  | M |  |  | H
1.3 Commission peer review of stock assessment | Research agency; Management agency | 12 mths | H | M |  | M |  |  | H
1.4 Review data collection and sampling protocols | Research agency; client organisation | 18 mths |  |  |  |  | L | L
2. Habitats and ecosystems
2.1 Review habitat impacts | Fishery science consultant | [17 empty] | M
2.2 Review of ecosystem literature and produce report | Fishery science consultant | [20 empty] | M
3. Enforcement (MCS)
3.1. Formalize designated landing sites | Client organisation; Enforcement agency |  |  |  |  | H
3.2. Develop surveillance programme at landing sites (e.g. random & targeted checks) | Enforcement agency |  |  |  |  | H |  | M |  |  |  | M |  |  | M |  |  | M | [12 empty] | H
3.3 Employ and train additional enforcement officers | Enforcement agency | [6 empty] | M | [22 empty] | H
3.4 Review existing MCS strategy | Enforcement agency; management agency |  |  |  |  | H
3.5 Compile data on MCS activities (e.g. number of surveillance patrols, infringements) | Enforcement agency | [29 empty] | M |  | M
4. Management and governance
4.1 Review of fisheries legislation, fines & penalties | Management agency; management partners / advisory group | [23 empty] | M
4.2 Review of national and international management measure and their effectiveness | Management agency; management partners / advisory group | [23 empty] | M
4.3 Document existing efforts to demonstrate effective process exists | Management agency; management partners / advisory group | [24 empty] | M
4.4 Seek letter of support from stakeholders to encourage adoption of FMP | Client organisation; NGOs | [25 empty] | L |  | L
4.5 Develop research plan | Client organisation; research agency; management agency; NGOs | [30 empty] | M
Notes: assumption is that 'client organisation' in this hypothetical case is a fishery group (e.g., a fisher's association; industry group; or fishery community association)

## Action Plan Cross-Ref Template
ACTION / TASK | ACTION LEAD & PARTNERS | TIMEFRAME | Links to MSC Performance Indicators
|  |  | P1. Target stocks | [6 empty] | P2. Ecosystem components | [14 empty] | P3. Management system
|  |  | 1.1.1 Stock status | 1.1.2 Reference points | 1.1.3 Stock rebuilding | 1.2.1 Harvest Strategy | 1.2.2 Harvest control rules and tools | 1.2.3 Information and monitoring | 1.2.4 Assessment | 2.1.1 Retained spp. status | 2.1.2 Retained spp. management | 2.1.3 Retained spp: Information & monitoring | 2.2.1 Bycatch spp. status | 2.2.2 Bycatch spp. management | 2.2.3. Bycatch spp: Information & monitoring | 2.3.1 ETP spp. status | 2.3.2 ETP spp. management | 2.3.3 ETP spp: Information & monitoring | 2.4.1 Habitat status | 2.4.2 Habitat strategy | 2.4.3 Habitat: information & monitoring | 2.5.1 Ecosystem: status | 2.5.2 Ecosystem: strategy | 2.5.3 Ecosystem: information & monitoring | 3.1.1 Legal or customary framework | 3.1.2 Consultation, roles & responsibilities | 3.1.3 Long-term objectives | 3.1.4 Incentives for sustainable fishing | 3.2.1 Fishery-specific objectives | 3.2.2 Decision-making processes | 3.2.3 Compliance & enforcement | 3.2.4 Research plan | 3.2.5 Management performance evaluation
1. [insert high level issue] |  |  | (note: H = high priority, M = medium priority, L = low priority according to MSC pre-assessment)
1.1
1.2
1.3
1.4
2. [insert high level issue]
2.1
2.2
3. [insert high level issue]
3.1.
3.2.
3.3
3.4
3.5
4. [insert high level issue]
4.1
4.2
4.3
4.4
4.5
NOTES:
1. Insert or delete issues according to the needs of your action plan.
2. Insert or delete lines and numbers (1.1, 1.2, etc) according to the needs of your plan.
3. Denote H, M, or L priority by colouring relevant boxes under the Performance Indicator: |  |  | H |  | M |  | L
4. Cross-reference each action to as many corresponding Performance Indicators as are relevant in your action plan.